## NEW Production Summary
APPENDIX B - PRODUCTION SUMMARY
DATE | FIELD ACTIVITIES AND OBSERVATIONS | PROCESSOR COMMENTS AND OBSERVATIONS | LINE | LINE START | LINE END | TX START | TX END | READ (km)
[8 empty] | MT | IP | IP CURRENT EXTENSIONS
Ketza Project CA00681T- Production Summary
2009-07-09 | Mob from Whitehorse to Ketza Mine camp | Mob from Whitehorse to Ketza Mine camp
2009-08-10 | Setup infinite, GPS & picket part of line, do PST & setup remote | Setup infinite, GPS & picket part of line, do PST & setup remote
2009-08-11 | Finish GPS & picketting first line & part of 2nd line; setup line, and waited for batteries from the truck that broke down in Whitehorse | Finish GPS & picketting first line & part of 2nd line; setup line, and waited for batteries from the truck that broke down in Whitehorse
2009-08-12 | Read IP & MT | Read IP & MT | L0N | 0E | 2400E | 650W | 3050E | 2.4 | 0.1 | 0.7
2009-08-13 | Read IP | Read IP | L0N | 0E | 2400E | 650W | 3050E |  | 2.3 | 0.6
2009-08-14 | Move to L600N, Start IP and MT | Read 7 Tx's for IP, Start MT | L600N | 0E | 2400E | 650W | 3050E |  | 0.2 | 0.3
2009-08-15 | Continue reading IP and MT | More LF MT events needed due to noisy results from the previous night | L600N | 0E | 2400E | 650W | 3050E | 2.4 | 2.2 | 1
2009-08-16 | Pick up L600N and start GPS & picket of L400N | Pick up L600N and start GPS & picket of L400N
2009-08-17 | Start Setup of L400N. Not finished due to dangerous conditions & falling rocks. | Start setup of L400N.
2009-08-18 | Start reading IP and read MT | Start reading IP and read MT | L400N | 0E | 2400E | 650W | 3050W | 2.4 | 0.4 | 0.3
2009-08-19 | Finish IP, picket L200N | Finish IP, picket L200N | L400N | 0E | 2400E | 650W | 3050W |  | 2 | 1
2009-08-20 | L200N deemed too dangerous, pick up gear from the field and pack up trucks | L200N deemed too dangerous, pick up gear from the field and pack up trucks
2009-08-21 | De-mob to Whitehorse | De-mob to Whitehorse
| TOTAL SURVEY COVERAGE (KM) AND CHARGE |  |  | 0 |  |  |  | 7.2 | 7.2 | 3.9