## Shafting Results
Shaft ID | Start Date | End Date | Northing | Easting | Total Depth | Au_mg
19S-SHP-01 | 2019-04-09 | 2019-04-11 | 07 V 581866 | 6961845 | 11'
From_ft | To_ft | Material | Estimated Rock Size | Estimated Weight | Color
0 | 6 | Muck | - | - | Black | 0
6 | 7.5 | gravel |  |  |  | 12
7.5 | 8.5 | boulders, gravel | 1.5' x 1' x 8'' |  |  | 19
8.5 | 9.9 | boulders, gravel | 1.5' x 1' x 8'' |  |  | 8
9.9 | 11 | bedrock, silty - clay |  |  | grey | 5
Shaft ID | Start Date | End Date | X Coordinate | Y Coordinate | Total Depth | Au_mg
19S-SHP-02 | 2019-04-09 | 2019-04-12 | 07 V 0581884 | 6961878 | 10.5'
From_ft | To_ft | Material | Estimated Rock Size | Estimated Weight | Color
0 | 0.5 | organic | - | - | black | 0
0.5 | 2.5 | Boulders, fluvial | 40cm | 5lb- 150lb | grey, brown | 0
2.5 | 3.5 | Boulders, gravel, fluvial | 30cm | 30lb | grey rocks. | 12
3.5 | 4.5 | Boulders, gravel, fluvial | 30cm | 30lb | grey rocks. | 110
4.5 | 5.5 | Boulders, gravel, fluvial | 30cm | 25lb | grey rocks. | 60
5.5 | 6.5 | Boulders, gravel, fluvial | 30cm | 20lb | grey rocks. | 156
6.5 | 7.5 | Boulders, gravel, fluvial | 30cm | 20lb | grey rocks. | 46
7.5 | 8.5 | Boulders, gravel, fluvial | 30cm | 20lb | grey rocks. | 21
8.5 | 9.5 | clay |  |  | orange | 2
9.5 | 10.5 | Bedrock on east wall | 3 cm - 20 cm | 20lb | grey, dark grey | 4
Shaft ID | Start Date | End Date | X Coordinate | Y Coordinate | Total Depth | Au_mg
19S-SHP-03 | 2019-04-12 | 2019-04-16 | 07 V 581943 | 6961798 | 12.5'
From_ft | To_ft | Material | Estimated Rock Size | Estimated Weight | Color
0 | 4 | muck | - | - | black | 0
4 | 7 | sand gravel |  |  |  | 1
7 | 8.5 | large boulder, gravel |  |  |  | 12
8.5 | 10 | large boulder, gravel |  |  |  | 10
10 | 10.7 | large boulder, gravel |  |  |  | 9
10.7 | 11.7 | large boulder, gravel |  |  |  | 15
11.7 | 12 | transition zone from gravel to bedrock. |  |  | grey | 200
12 | 12.5 | Bedrock |  |  |  | 6
Shaft ID | Start Date | End Date | X Coordinate | Y Coordinate | Total Depth | Au_mg
19S-SHP-04 | 2019-04-13 | 2019-04-16 | 07 V 0581809 | 6961900 | 10'4"
From_ft | To_ft | Material | Estimated Rock Size | Estimated Weight | Color
0 | 0.8 | organic | - | - | dark brown/black | 0
0.8 | 2.5 | sand, boulders | 10cm up to 90cm | 30 |  | 0
2.5 | 5.5 | gravel, boulders | 20cm up to 80cm | 30 |  | 0
5.5 | 6.5 | gravel, boulders | 20cm up to 80cm | 30 |  | 20
6.5 | 7.5 | gravel, boulders | 20cm up to 80cm | 30 |  | 19
7.5 | 8.5 | gravel, boulders | 20cm up to 80cm | 30 |  | 23
8.5 | 9.5 | gravel, boulders | 20cm up to 80cm | 30 |  | 52
9.5 | 10.5 | Bedrock |  | 30 |  | 25
Shaft ID | Start Date | End Date | X Coordinate | Y Coordinate | Total Depth | Au_mg
19S-SHP-05 | 2019-04-18 | 2019-04-20 | 07 V 0581355 | 6963021 | 10'5''
From_ft | To_ft | Material | Estimated Rock Size | Estimated Weight | Color
0 | 0.5 | organic |  |  |  | 0
0.5 | 2.5 | muck w organic |  |  |  | 0
2.5 | 3 | gravel | 8'' |  |  | 2
3 | 5.5 | muck |  |  |  | 0
5.5 | 6.5 | gravel | 6'' |  |  | 0
6.5 | 7.5 | White layer. ash? |  |  | white | 0
7.5 | 8.5 | big stones | 1.5' - 8'' |  |  | < 1
8.5 | 9.7 | gravel | 6-8'' |  |  | 0
9.7 | 10 | clay | grey |  |  | 5
10 | 10.5 | bedrock |  |  |  | < 1

## Shaft Thawing
2019 Shaft Thawing Tracker
Shaft ID | X Coordinate | Y Coordinate | Boiler Size | Delivery Method
19S-SHP-01 |  |  | 91 liters | Single Point
Start Time | End Time | Depth Thawed | Point Style | Depth Placed | Pattern Used | Temperature/Depth | Water Used | Final Shaft Size | Consumables | Pressure: | Blow out Valve rating:
Played around in hole too much to keep exact time
2019 Shaft Thawing Tracker
Shaft ID | X Coordinate | Y Coordinate | Boiler Size | Delivery Method
19S-SHP-02 |  |  | 91 Liters | Single Point
Start Time | End Time | Depth Thawed | Point Style | Depth Placed | Pattern Used | Temperature/Depth | Water Used | Final Shaft Size | Consumables | Pressure: | Blow out Valve rating:
2019-04-10 09:30 | 2019-04-10 11:00 | 30'' | single | 30'' | single center point |  | 80L | 3.5x4 |  | 20psi | 30
2019-04-10 16:00 | 2019-04-10 19:00 | 4' | single | 4' | single center point |  | 80L | 3.5x4 |  | 15-20psi | 30
2019-04-11 15:50 | 2019-04-11 19:00 | 5' | single | 4' | single center point |  | 80L | 2.5ft |  |  | 30
2019 Shaft Thawing Tracker
Shaft ID | X Coordinate | Y Coordinate | Boiler Size | Delivery Method
19S-SHP-03
Start Time | End Time | Depth Thawed | Point Style | Depth Placed | Pattern Used | Temperature/Depth | Water Used | Final Shaft Size | Consumables | Pressure: | Blow out Valve rating:

## Personnel Tracker
2019 Shafting Personnel | March | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | May | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
| 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Resupply Dates | bar: Thu 11; Fri 19
YARD WORK
Shawn Ryan
Simon Cash | Sun 31: Prep; Mon 1: Prep; Tue 2: Prep; Wed 3: Prep; Thu 4: Prep; Fri 5: Prep; Wed 24: Data; Fri 26: Inventory; Sat 27: SOP
Tyler Palmer | Tue 2: Prep; Wed 3: Prep; Thu 4: Prep; Fri 5: Prep; Sat 6: Prep; Sun 7: Prep; Wed 24: research
Claude
Kalisha Johnson | Wed 10: Prep
Travel Days
Shawn Ryan | Thu 4: WH-DC
Simon Cash | Sat 30: WH-DC
Tyler Palmer | Mon 1: Travel; Tue 2: WH-DC; Thu 25: Travel
Claude
Kalisha Johnson | Mon 8: Travel; Tue 9: Travel; Wed 24: Travel
Field Work
Shawn Ryan | Fri 5: SHP; Mon 8: MOAB; Tue 9: SHP-S1; Wed 10: SHP-S1; Thu 11: SHP-S1; Fri 12: SHP-S3; Sat 13: SHP-S3; Sun 14: SHP-S3; Mon 15: SHP-S3; Tue 16: SHP-S3; Wed 17: SHP-Drill; Thu 18: Demobe
Simon Cash | Mon 8: MOAB; Tue 9: SHP-S2; Wed 10: SHP-S2; Thu 11: SHP-S2; Fri 12: SHP-S2; Sat 13: SHP-S4; Sun 14: SHP-S4; Mon 15: SHP-S3; Tue 16: SHP-S4; Wed 17: SHP-Drill; Thu 18: SHP-S5; Fri 19: SHP-S5; Sat 20: SHP-S5; Sun 21: SHP-CMP; Mon 22: SHP-CMP; Tue 23: Demobe; Thu 25: SHP-Demobe
Tyler Palmer | Fri 5: SHP; Mon 8: MOAB; Tue 9: SHP-S2; Wed 10: SHP-S2; Thu 11: SHP-S2; Fri 12: SHP-S2; Sat 13: SHP-S4; Sun 14: SHP-S4; Mon 15: SHP-S4; Tue 16: SHP-S4; Wed 17: SHP-Drill; Thu 18: SHP-S5; Fri 19: SHP-S5; Sat 20: SHP-S5; Sun 21: SHP-CMP; Mon 22: SHP-CMP; Tue 23: Demobe
Claude | Mon 8: MOAB; Tue 9: SHP-S1; Wed 10: SHP-S1; Thu 11: SHP-S1; Fri 12: SHP-S3; Sat 13: SHP-S3; Sun 14: SHP-S3; Mon 15: SHP-S4; Tue 16: Demobe
Kalisha Johnson | Thu 11: MOAB; Fri 12: SHP-Cook; Sat 13: SHP-Cook; Sun 14: SHP-Cook; Mon 15: SHP-Cook; Tue 16: SHP-Cook; Wed 17: SHP-Cook; Thu 18: SHP-Cook; Fri 19: SHP-Cook; Sat 20: SHP-Cook; Sun 21: SHP-Cook; Mon 22: SHP-Cook; Tue 23: Demobe
Note on I13: Medicine Hat to Whitehorse
Note on AG13: DC-Medicne hat
Note on Q15: arrive in DC
Note on AF15: DC to victoria
Note on M17: Scouting daytrip to shovel
Note on AG18: go in with drone crew and demode remaining shovel camp
Note on M19: Scouting daytrip to shovel
Note on S21: Flys into camp from DC

## Fuel Tracker
2019 Shafting Fuel Tracker | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | May | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
| 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Daily Diesel Used | Fri 5: 0; Sat 6: 0; Sun 7: 0; Mon 8: 0; Tue 9: 0; Wed 10: 0; Thu 11: 0; Fri 12: 0; Sat 13: 0; Sun 14: 0; Mon 15: 0; Tue 16: 0; Wed 17: 0
Full Diesle Drums on Site | Fri 5: 6
Empty Drums on Site | bar: Fri 5 to Fri 31
Diesel Drums Delivered
Empty Diesel Drums Removed
Comtaminated Diesel Drums
Jet A Used
Full Jet A Drums | bar: Fri 5
Empty Jet A Drums | bar: Fri 5 to Fri 31
Jet A Delivered
Empty Jet A Drums Removed
Contaminated Jet A Drums
Gasoline Used (Liters)
Full Gasoline Drums | bar: Fri 5
Empty Gasoline Drums
Gasoline Drums Delivered
Gasoline Jerry Cans Delivered
Gasoline Drums Removed
Contaminated Gasoline Drums
Total Diesel Drums Used on Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Jet A Used on Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Gasoline Used on Project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Daily Worksite Shaft Log Templa
|  | 2019 Daily Log Shaft Thawing Tracker |  |  |  | fill out during the day and return to supervisor at end of day to input into Tracker.
Shaft ID |  | Shafters: |  | Delivery Method: |  | Date:
Start Time | End Time | Depth Thawed | Point Style | Depth Placed | Temperature/ Depth (Degree/FT) |  | Pipe Material | Pattern Used | Final Shaft Size | Water QTY Used(L) | Pressure readings:
COMMENTS:
Consumables Used During Day:
End Of Day Depth:
Remember to take Photo's of the shaft site, material, inside of shaft and any other findings AT END OF DAY